## Worksheet
Logistics Planning - Time Tracker (Client View)
Task ID | Task Description | Planned Start Date | Planned End Date | Status | Assigned To | Actual Start Date | Actual End Date | Billed Hours (Est.) | Billed Hours (Act.)
TASK-001 | Initial Site Assessment & Documentation | 2025-04-01 | 2025-04-03 | In Progress | John Doe (Logistics Lead) | 2025-04-01 | -- | 8 | 6.5
TASK-002 | Route Planning & Optimization Analysis | 2025-04-04 | 2025-04-06 | Pending | Jane Smith (Route Analyst) | -- | -- | 12 | 0
TASK-003 | Carrier Coordination & Contract Finalization | 2025-04-07 | 2025-04-11 | Pending | Mike Brown (Vendor Manager) | -- | -- | 16 | 0
Total Estimated Hours: | [8 empty] | 36
Total Actual Hours: | [8 empty] | 6.5