## Worksheet
Logistics Planning - Time Tracker Dashboard
Real-time tracking of shipment schedules, delivery timelines, and resource allocation
Task ID | Activity Description | Assigned To | Start Date | End Date | Status | Duration (Days)(Planned/Actual)
LP-T001 | Procure raw materials - Supplier A | Jane Smith | 2025-04-01 | 2025-04-15 | In Progress | 15 / 9(+6)
LP-T002 | Transportation dispatch - Region East | Robert Lee | 2025-04-18 | 2025-04-30 | In Progress | 13 / 7(+6)
LP-T003 | Warehouse loading - Distribution Center 2 | Lisa Wang | 2025-04-15 | 2025-04-18 | Completed | 4 / 3(+1)
LP-T004 | Delivery route optimization - Route X57 | Daniel Kim | 2025-04-19 | 2025-04-23 | Pending Start | 5 / 0(+5)
LP-T005 | Customs documentation - Export Zone B | Maria Gonzalez | 2025-04-17 | 2025-04-19 | Completed | 3 / 3(+0)
LP-T006 | Final inspection - Quality Assurance Unit | Alex Johnson | 2025-04-18 | 2025-04-19 | Completed | 2 / 1.5(+0.5)
LP-T007 | Carrier handover - Logistics Hub Delta | Nina Patel | 2025-04-21 | 2025-04-30 | Pending Start | 10 / 0(+10)
LP-T008 | Customer delivery - Prime Client Contract #789 | Tyler Brown | 2025-04-24 | 2025-04-30 | Pending Start | 7 / 0(+7)
Dashboard Summary:3 Tasks In Progress ¦ 3 Completed ¦ 2 Pending
Last updated: April 5, 2025 • Data refreshed in real time