## Worksheet
Logistics Planning - Time Tracker (Detailed)
Date | Activity Type | Project / Route ID | Planning Phase |  |  | Execution Phase |  |  | Monitoring & Adjustment
|  |  | Planned Start Time | Planned End Time | Assigned Team Member(s) | Actual Start Time | Actual End Time | Status (On/Off Track) | Audit Notes / Delays | Last Updated By
2024-04-01 | Route Planning & Optimization | RTP-7892 | 08:30 AM | 11:30 AM | Alice Johnson, Mark Lee | - | - | Pending Start | Route analysis in progress; GPS data integration delayed. | Alice Johnson
2024-04-01 | Inventory Loading Coordination | INV-LD331 | 10:00 AM | 12:30 PM | Sarah Kim, Tom Wilson | - | - | Pending Start | Packing schedule delayed due to missing pallets. | Tom Wilson
2024-04-01 | Truck Dispatch & Routing Finalization | TDF-5567 | 12:30 PM | 01:30 PM | Alex Rivera, Emily Chen | - | - | Pending Start | Waiting on weather forecast approval. | Emily Chen
2024-04-01 | Real-Time Tracking Setup (GPS & Telematics) | TSTK-8891 | 09:00 AM | 11:30 AM | Lisa Park, James Wong | 09:25 AM | 11:45 AM | On Track | Minor delay in device calibration; resolved within 15 mins. | Lisa Park
2024-04-01 | Delivery Schedule Confirmation (Client) | DSC-3389 | 01:30 PM | 02:15 PM | Alice Johnson, Mark Lee | 01:45 PM | 02:25 PM | Slight Delay (10 mins) | Calls delayed due to client’s meeting conflict. | Mark Lee
Daily Summary (2024-04-01) | [9 empty] | —
2024-04-02 | Route Replanning (Due to Weather) | RTP-7893 | 08:00 AM | 10:30 AM | Alice Johnson, Sarah Kim | - | - | Pending Start (Weather Alert) | Storm warning issued; awaiting official all-clear. | Sarah Kim
Daily Summary (2024-04-02) | [9 empty] | —
Note: All times are in local time. Status indicators: Green = On Track, Yellow = Slight Delay, Red = Major Delay. Updates should be made daily before 5 PM.