## Worksheet
Task ID | Task Description | Assigned To | Priority | Due Date | Status | Notes/Comments
TL-001 | Confirm shipping carrier for Q3 deliveries | John Smith | High | 2024-11-15 | Pending | Contacted three carriers; waiting for final quote.
TL-002 | Update warehouse inventory system with new stock batch | Emily Chen | Medium | 2024-11-18 | In Progress | Batch #WV7893 imported; validation pending.
TL-003 | Arrange customs documentation for international shipment to Berlin | Carlos Mendez | High | 2024-11-20 | Pending | Required certificates need approval from legal team.
TL-004 | Coordinate truck dispatch schedule with regional logistics hubs | Sarah Johnson | High | 2024-11-16 | Completed | All routes confirmed; drivers notified.
TL-005 | Review and approve supplier delivery timelines for December | David Lee | Medium | 2024-11-30 | Pending | Awaiting updated forecasts from procurement.
TL-006 | Conduct safety audit of fleet vehicles before year-end inspection | Michael Brown | High | 2024-11-25 | In Progress | Completed 5 out of 8 vehicles; next inspection scheduled for Friday.