## Worksheet
Logistics Planning - To-Do List (Planning View)
Track and manage logistics tasks with priority, status, and timeline details
Task ID | Task Description | Priority | Status | Assigned To | Due Date | Pipeline Stage (ETA)
T001 | Finalize shipping routes for Q3 deliveries | High | In Progress | Jane Smith | 2024-06-15 | Route Confirmation - 2024-06-18
T002 | Procure additional warehouse space in Chicago | Medium | In Progress | Mark Johnson | 2024-06-30 | Rental Agreement Signed - 2024-06-19
T003 | Update inventory tracking system with real-time GPS integration | High | Delayed | Emily Chen | 2024-06-10 | Scheduled for 2024-06-17 (Postponed)
T004 | Train warehouse staff on new loading procedures | Medium | Completed | Robert Davis | 2024-05-31 | Training Completed - 2024-05-31
T005 | Negotiate fuel surcharge agreements with carriers | Low | In Progress | Lisa Wong | 2024-07-15 | Negotiation Phase - 2024-07-18
Total Tasks: | [5 empty] | 5