## Worksheet
Week | Task | Owner | Status | Start Date | Due Date | Completion % | Notes
Week 1 | Social Media Campaign Launch | Marketing Team A | Not Started | 2024-06-03 | 2024-06-10 | 0% | Awaiting creative assets
Week 2 | Email Newsletter Distribution | Marketing Team B | In Progress | 2024-06-10 | 2024-06-17 | 50% | Draft approved, awaiting final review
Week 3 | Influencer Outreach | Marketing Team C | Completed | 2024-06-17 | 2024-06-24 | 100% | 5 influencers confirmed
Week 4 | Ad Performance Analysis | Analytics Team | Not Started | 2024-06-24 | 2024-07-01 | 0% | Data collection pending
Week 5 | A/B Testing - Landing Pages | UX Team | Not Started | 2024-07-01 | 2024-07-08 | 0% | Designs in review