## Worksheet
Week | Objective | Campaign Name | Channel | Budget ($) | Start Date | End Date | Responsible Team | KPI Target | Actual Performance | Status | Notes
1 | Brand Awareness | Launch Campaign Q3 | Social Media | 50,000 | 2024-07-01 | 2024-07-31 | Digital Marketing | 5M Impressions | 4.8M | On Track | High engagement on Instagram.
2 | Lead Generation | Webinar Series | Email + LinkedIn | 30,000 | 2024-08-05 | 2024-08-31 | Sales & Marketing | 2,500 Leads | 2,300 | Slight Delay | Low registration rate.
3 | Customer Retention | Loyalty Program Launch | App + SMS | 20,000 | 2024-08-15 | 2024-09-30 | Customer Success | 40% Retention Increase | 35% | On Track | Early adopters showing high satisfaction.
4 | Market Expansion | Regional Ad Blitz | TV + Programmatic Display | 80,000 | 2024-09-01 | 2024-10-31 | Media Planning | 500K New Markets Reached | 420K | Delayed | Supply chain affected ad placement.
5 | Product Launch | New Feature Rollout | Influencer + PR | 60,000 | 2024-10-05 | 2024-11-30 | Product Marketing | 50K Sign-ups | 48K | On Track | Strong media coverage.
6 | Performance Review | Q3 Analytics Report | Internal Dashboard | 5,000 | 2024-10-31 | 2024-11-30 | Analytics Team | ROAS ≥ 5.0 | 4.92 | Near Target | Slight drop in CTR on retargeting.