## Worksheet
Task | Start Date | End Date | Duration (Days) | Progress (%) | Owner | Status | Gantt Bar
Brand Awareness Campaign | 2024-03-01 | 2024-03-31 | 31 | 75% | Marketing Team | In Progress
Social Media Blitz | 2024-03-15 | 2024-04-15 | 31 | 40% | Digital Team | In Progress
Email Marketing Series | 2024-03-10 | 2024-04-10 | 31 | 90% | Content Team | Almost Complete
Influencer Partnerships | 2024-03-25 | 2024-05-15 | 51 | 15% | PR Team | Not Started
Analytics & Reporting | 2024-04-01 | 2024-04-30 | 30 | 0% | Analytics Team | Not Started