## Worksheet
Task | Start Date | End Date | Duration (Days) | Progress (%) | Status | Owner
Market Research | 2024-06-01 | 2024-06-15 | 15 | 100 | Completed | Alex Rivera
Brand Identity Design | 2024-06-16 | 2024-07-05 | 20 | 75 | In Progress | Jamie Chen
Social Media Campaign | 2024-07-06 | 2024-07-31 | 26 | 0 | Not Started | Taylor Kim
Email Marketing Setup | 2024-07-01 | 2024-07-15 | 15 | 50 | In Progress | Casey Morgan
Launch Event | 2024-08-01 | 2024-08-10 | 10 | 0 | Not Started | Jordan Lee