## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Owner
Market Research | 2024-06-01 | 2024-06-15 | 15 | Completed | Alice Johnson
Campaign Design | 2024-06-16 | 2024-06-30 | 15 | In Progress | Bob Smith
Social Media Launch | 2024-07-01 | 2024-07-15 | 15 | Pending | Carol Davis
Email Marketing | 2024-07-16 | 2024-07-31 | 16 | Pending | Dave Wilson
Analytics & Reporting | 2024-08-01 | 2024-08-15 | 15 | Pending | Eve Brown
Total Duration (Days): |  |  | 76 | Report Version - Marketing Plan Gantt Chart