## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Priority | Budget ($) | Progress (%) | Notes
1 | Market Research Analysis | Jane Doe | 2024-06-01 | 2024-06-15 | Completed | High | 5,000.00 | 100 | Survey data collected from 5 regions.
2 | Social Media Campaign Launch | John Smith | 2024-06-16 | 2024-07-31 | In Progress | High | 12,000.00 | 45 | Ads running on Instagram and LinkedIn.
3 | Email Marketing Automation | Alex Rivera | 2024-06-20 | 2024-07-15 | Not Started | Medium | 3,500.00 | 0 | Template design pending approval.
4 | Influencer Partnerships | Maria Chen | 2024-07-01 | 2024-08-31 | Not Started | High | 15,000.00 | 0 | Outreach to top 20 influencers.
5 | Q3 Performance Report | Robert Kim | 2024-09-01 | 2024-09-15 | Not Started | High | 2,000.00 | 0 | Includes ROI analysis and recommendations.