## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Budget ($) | Priority | KPI Target
1 | Market Research Analysis | Sales Team | 01/04/2024 | 30/04/2024 | In Progress | 15,000 | High | 95% Accuracy Rate
2 | Campaign Development (Digital) | Digital Marketing Dept. | 01/05/2024 | 15/05/2024 | Not Started | 45,000 | High | +30% Engagement Rate
3 | Campaign Development (Traditional) | Brand Management Dept. | 16/05/2024 | 31/05/2024 | Not Started | 35,000 | Moderate | +15% Brand Recall
4 | Influencer Partnerships | PR & Communications Team | 01/06/2024 | 15/06/2024 | Not Started | 30,000 | High | +5% Conversion Rate
5 | Campaign Launch & Monitoring | Marketing Operations Team | 16/06/2024 | 30/08/2024 < | Not Started | 55,000 | High | +45% Lead Generation
6 | Post-Campaign Analysis & Reporting | Data Analytics Team | 01/09/2024 | 15/09/2024 | Not Started | 18,000 | Moderate | ROI of 5:1 or Greater
Total Budget: | [5 empty] | $198,000