## Worksheet
Task | Owner | Start Date | End Date | Status | Budget ($) | Notes
Market Research | Marketing Team | 2024-06-01 | 2024-06-15 | Completed | 5,000 | Survey conducted across 3 regions
Campaign Design | Creative Team | 2024-06-16 | 2024-06-30 | In Progress | 12,000 | Social media and email templates ready
Ad Launch | Digital Team | 2024-07-01 | 2024-07-15 | Not Started | 25,000 | Google Ads, Facebook, LinkedIn
Analytics & Reporting | Data Team | 2024-07-16 | 2024-07-31 | Not Started | 3,000 | Track CTR, conversions, ROI
Final Review & Optimization | Marketing Director | 2024-08-01 | 2024-08-15 | Not Started | 2,000 | Adjust budget allocation based on results
Total Budget: |  |  |  |  | $47,000