## Worksheet
Task | Owner | Start Date | End Date | Status | Priorities | Budget ($) < th>Notes
Market Research | Marketing Team | 2024-06-01 | 2024-06-15 | In Progress | High | 5,000 | Gather customer feedback via surveys and focus groups.
Social Media Campaign | Social Media Manager | 2024-06-16 | 2024-07-31 | Not Started | High | 8,000 | Create content calendar and run ads on Facebook & Instagram.
Email Newsletter Launch | Email Specialist | 2024-06-20 | 2024-07-15 | Not Started | Medium | 3,500 | Create 3 monthly newsletters with promotional offers.
Partnership Outreach | Business Development | 2024-07-01 | 2024-08-31 | In Progress | Medium | 6,000 | Secure 5 co-marketing partnerships with complementary brands.
Campaign Analysis & Reporting | Data Analyst | 2024-08-01 | 2024-08-31 | Not Started | High | 2,500 | Evaluate ROI and deliver final performance report.
Marketing Plan – Project Plan (Planning View) ¦ Updated: June 2024