## Worksheet
Task | Owner | Start Date | End Date | Status | Budget (USD) | KPIs | Notes
Brand Awareness Campaign | Marketing Team | 2024-06-01 | 2024-08-31 | Planning | $75,000 | Reach: 5M, Engagement Rate: 4.5% | Include social media influencers and programmatic ads
Email Marketing Automation | Digital Marketing | 2024-07-01 | 2024-09-30 | In Progress | $35,000 | Open Rate: 28%, CTR: 6.2% | Segment audiences by purchase behavior
Trade Show Participation | Events Team | 2024-08-15 | 2024-10-30 | Upcoming | $95,000 | Leads Generated: 800, Conversion Rate: 25% | Booth design approved; VIP client invites scheduled
Content Marketing Series | Content Team | 2024-06-15 | 2024-12-31 | In Progress | $50,000 | Blog Views: 250K, Downloads: 4K | Weekly blogs + downloadable whitepapers
Paid Search (PPC) | SEO & SEM Team | 2024-06-01 | 2024-12-31 | In Progress | $85,000 | CPC: $2.20, ROI: 4.8x | A/B test landing pages monthly
Partnership Campaigns | Business Dev | 2024-07-15 | 2024-11-30 | Planning | $45,000 | Co-branded Leads: 350, CAC Reduction: -18% | Targeting top 3 strategic partners
Analytics & Reporting Dashboard | Data Team | 2024-06-25 | 2024-08-31 | In Progress | $25,000 | Real-time KPI tracking, Weekly reports | Integration with CRM and GA4 required