## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Budget ($) | Progress (%)
Market Research | Jane Doe | 2024-01-15 | 2024-01-30 | Completed | High | 5,000 | 100
Campaign Design | John Smith | 2024-02-01 | 2024-02-15 | In Progress | High | 8,000 | 65
Social Media Launch | Alex Brown | 2024-02-16 | 2024-03-15 | Not Started | Medium | 12,000 | 0
Email Campaign | Sarah Lee | 2024-03-16 | 2024-03-31 | Not Started | High | 6,500 | 0
Analytics & Reporting | Mike Wilson | 2024-04-01 | 2024-04-15 | Not Started | Medium | 3,500 | 0