## Worksheet
Task | Owner | Start Date | End Date | Status | Priorities | Budget ($) | Dependencies | Notes / Remarks
Market Research Analysis | Sales Team | 2024-01-15 | 2024-01-30 | Completed | High | 5,000 | - | Data collected from 3 regions.
Brand Awareness Campaign | Marketing Team | 2024-02-01 | 2024-03-15 | In Progress | High | 15,000 | Market Research Completion | Social media + influencer collabs planned.
Email Marketing Setup | Digital Team | 2024-02-10 | 2024-02-28 | Pending | Medium1,558.96,733.96:0
Launch Event (Virtual) | Event Team | 2024-03-20 | 2024-03-31 | Pending
Total Budget Allocated: | [5 empty] | $21,500