## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Budget ($) | Notes
Market Research & Analysis | Marketing Team | 2024-06-01 | 2024-06-30 | Completed | High | 25,000 | Survey data collected from target segments
Campaign Strategy Development | Strategy Director | 2024-07-01 | 2024-07-15 | In Progress | High | 20,000 | Align with Q3 brand positioning
Digital Ads Launch | Digital Team | 2024-07-16 | 2024-08-31 | Not Started | High | 75,000 | Google Ads, Meta, LinkedIn
Email Marketing Campaign | CRM Team | 2024-07-20 | 2024-08-31 | Not Started | Medium | 15,000 | Segmented by customer lifecycle stage
Influencer Partnerships | PR Team | 2024-07-25 | 2024-09-30 | Not Started | Medium | 40,000 | Engage top 25 micro-influencers
Event Sponsorship (Trade Show) | Events Manager | 2024-08-01 | 2024-08-31 | Not Started | High | 50,000 | Annual Industry Expo, Booth #A7
Performance Analytics & Reporting | Analytics Team | 2024-09-01 | 2024-09-30 | Not Started | High | 10,000 | ROAS, CAC, conversion metrics
Final Review & Recommendations | Chief Marketing Officer | 2024-10-01 | 2024-10-07 | Not Started | High | 5,000 | Strategic insights for Q4 planning