## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Notes
Market Research | Marketing Team | 01/04/2024 | 15/04/2024 | Completed | High | Survey data collected from target demographics.
Campaign Design | Creative Team | 16/04/2024 | 30/04/2024 | In Progress | High | Social media creatives and email templates in development.
Media Buying | Digital Team | 01/05/2024 | 15/05/2024 | Not Started | High | Allocate budget across Google Ads and Meta platforms.
Launch Campaign | Marketing Team | 16/05/2024 | 31/05/2024 | Not Started | Critical | Full campaign rollout across all channels.
Performance Analysis | Analytics Team | 01/06/2024 | 15/06/2024 | Not Started | Medium | KPIs tracked; report to stakeholders.
Optimization Plan | Marketing Team | 16/06/2024 | 30/06/2024 | Not Started | High | Refine targeting and budget based on initial results.