## Worksheet
Task ID | Task Name | Owner | Department | Start Date | End Date | Status | Prioritization | Budget ($) | Actual Cost ($) | Variance ($) | Progress (%) | Notes
1 | Social Media Campaign Launch | Jane Doe | Marketing | 2024-03-01 | 2024-03-31 | In Progress | High | 5,000 | 4,200 | -800 | 85% | Leveraging Instagram and TikTok influencers.
2 | Email Newsletter Redesign | John Smith | Marketing | 2024-03-10 | 2024-03-25 | Pending | Medium | 1,500 | 0 | 0 | 15% | New template with dynamic content blocks.
3 | SEO Optimization Project | Alex Chen | Digital Marketing | 2024-03-05 | 2024-04-15 | In Progress | High | 3,800 | 1,950 | -1,850 | 52% | Focusing on keyword clustering and backlink acquisition.
4 | Q2 Event Sponsorship | Sarah Lee | Events | 2024-04-01 | 2024-06-30 | Pending | High | 15,000 | 75%
Total Budget: | [7 empty] | $25,300 | $6,900 | -18,400 | 57%