## Worksheet
Task ID | Task Name | Department | Owner | Start Date | End Date | Status | Prioritization | Budget ($) | Actual Spend ($) | Variance ($) | Notes
1 | Q3 Social Media Campaign | Marketing | Jane Doe | 07/01/2024 | 09/30/2024 | In Progress | High | 50,000.00 | 32,567.89 | -17,432.11 | Leveraging influencer partnerships; track CTR weekly.
2 | Email Newsletter Redesign | Marketing | John Smith | 07/15/2024 | 08/31/2024 | Pending Start | Medium | 15,000.00 | 0 | -15,000.0₀ | New template to be approved by Legal.
3 | Product Launch Event (NYC) | Marketing | Maria Garcia | 08/01/2024 | 08/15/2024 | In Progress | High150,00₀.₀₀ | 76,893.35 | -73,106.65 | Venue confirmed; VIP invites sent.
4 | Google Ads Optimization | Marketing | Alex Turner | 07/01/2024Adjusting bid strategies based on ROI data.
5 | Brand Awareness Survey | Marketing | Sarah Lin | 07/20/20249,876.54d< -133.73d< Survey distributed to 10K customers.
6 | Content Calendar Q4 | Marketing | Medium8,₀₀₀.₅₃₀.ₒₒ< d> -8,ooo.53d< Drafting topics with Sales team.