## Worksheet
Week | Activity | Description | Owner | Start Date | End Date | Budget ($) | Status
1 | Market Research | Gather customer insights and competitor analysis | Marketing Team | 01/01/2024 | 07/01/2024 | 5,000 | In Progress
2 | Campaign Design | Create visuals and copy for digital and print ads | Design Team | 08/01/2024 | 14/01/2024 | 3,500 | Pending
3 | Email Campaign Launch | Send promotional emails to segmented lists | Email Team | 15/01/2024 | 21/01/2024 | 2,000 | Pending
4 | Social Media Ads | Run targeted ads on Facebook, Instagram, LinkedIn | Social Media Team | 22/01/2024 | 28/01/2024 | 4,500 | Pending
5 | Performance Analysis | Evaluate KPIs and ROI of all campaigns | Analytics Team | 29/01/2024 | 04/02/2024 | 1,500 | Pending
Total Budget: | [5 empty] | $16,500