## Worksheet
Marketing Planning - Asset Tracking Template
Multi-Page Asset Tracking Overview
Asset ID | Asset Name | Type | Status | Assigned To | Last Updated
MKT-001 | Brand Logo Package | Design Asset | In Use | Jane Doe (Marketing) | 2023-10-15
MKT-002 | Product Brochure (v3)Print Asset | On Hold | John Smith (Design) | 2023-10-18
MKT-003 | Social Media Kit 2024Digital Asset | Ready for Review | Lisa Chen (Content) | 2023-10-19
MKT-004 | Video Ad - Launch CampaignVideo Asset | In Production | Mike Johnson (Creative) | 2023-10-20
MKT-005 | Email Template Suite v2.1Email Asset | Approved | Sarah Wilson (Email Marketing) | 2023-10-17
Asset ID | Category | Description | Creation Date | Version | Status Reason
MKT-001 | Brand Identity | Full logo suite with alternate versions and style guidelines. | 2023-05-12 | v4.1 | In Use - Active Campaigns
MKT-002 | Promotional Material | Brochure for Q4 product launch with pricing and features.2023-08-15 | v3.0 | On Hold - Approval Pending from Legal
MKT-003 | Social Media Content | Creative assets for Instagram, LinkedIn, and TikTok campaigns.2023-10-15 | v2.4 | Ready for Review - Awaiting Feedback from PMO
MKT-004 | Video Production | Campaign video showcasing new product features and customer testimonials.2023-10-18 | v1.2 (In Progress) | In Production - Editing Stage Complete, Final Review Pending
MKT-005 | Email Marketing | Template suite for monthly newsletters and promotional emails.2023-09-10 | v2.1 (Approved) | Approved - Live in Production Environment
Asset ID | Task Description | Start Date | Due Date | Status | Dependencies
MKT-001 | Create Final Brand Guidelines Document | 2023-05-14 | 2023-05-28 | Completed | N/A (Baseline)
MKT-002 | Finalize Brochure Design & Layout2023-10-16 | 2023-10-18In Progress | MKT-001 (Brand Guidelines)
MKT-003 | Generate Social Media Visuals (72 images)2023-10-17 | 2023-10-24Pending Review | MKT-005 (Email Templates)
MKT-004 | Produce & Edit Campaign Video (65 seconds)2023-10-19 | 2023-11-03In Progress | MKT-005 (Final Assets), MKT-003 (Visuals)
MKT-005 | Deploy Email Templates to ESP Platform2023-11-01 | 2023-11-04Pending Execution | MKT-004 (Video Final), MKT-003 (Visuals)
Marketing Planning - Asset Tracking Template ¦ Version 1.2 ¦ Multi-Page Format
Generated on: 2023-10-25 ¦ Prepared by: Marketing Operations Team