## Worksheet
Marketing Planning - Data Version
Section | Objective | KPIs | Timeline | Budget Allocation ($) | Status
Market Research | Identify target audience segments and preferences. | User survey response rate ≥ 75%, Competitor benchmarking report completion. | Q1 2024 | 15,000 | In Progress
Brand Positioning | Define core brand message and competitive differentiation. | Stakeholder approval on brand guidelines, Messaging consistency score ≥ 90%. | Q1 2024 | 10,000 | Completed
Content Strategy | Create engaging and consistent content across platforms. | Monthly content output: 8 posts/platform, Engagement rate ≥ 5%. | Q2-Q4 2024 | 30,000 | In Progress
Digital Advertising | Drive traffic and conversions via paid channels. | CTR ≥ 2.5%, Conversion rate ≥ 3.8%, CPA ≤ $25. | Q2-Q4 2024 | 100,000 | In Progress
Email Marketing | Nurture leads and retain customers. | Open rate ≥ 45%, Click-through rate ≥ 8%, Unsubscribe rate ≤ 0.5%. | Q2-Q4 2024 | 18,000 | In Progress
Social Media Management | Build community and brand awareness. | Following growth: +15% MoM, Engagement rate ≥ 6%. | Q2-Q4 2024 | 25,000 | In Progress
Events & Promotions | Boost visibility and customer engagement. | Event attendance ≥ 300 attendees per event, Promo redemption rate ≥ 25%. | Q3 2024 | 45,000 | Planned
Performance Review & Optimization | Analyze results and refine strategy. | Monthly report delivery, 3+ actionable improvements per quarter. | Quarterly (Q2-Q4) | 12,000 | Planned