## Worksheet
Marketing Planning - Business Plan Template (Planning View)
Quarter | Objective | KPIs & Targets | Key Initiatives | Budget Allocation (USD) | Responsible Team/Person
Q1: Market Research & Foundation Building
Q1 - January to March | Conduct comprehensive market research and competitive analysis. | • 3 detailed competitor reports • 200+ customer surveys completed • SWOT analysis finalized | - Launch customer survey campaign - Analyze industry trends report - Map out target personas | $15,000 | Market Research Team - Jane Doe
Q1 - January to March | Develop core brand messaging and positioning. | • Brand identity guide completed • 3 messaging variants tested • Stakeholder approval secured | - Draft brand guidelines document - Run A/B testing on value propositions - Present to executive board | $10,000 | Brand Strategy Team - Mark Lee
Q2: Launch Preparation & Channel Setup
Q2 - April to June | Prepare for product/service launch with pre-launch campaigns. | • 5,000 leads generated • Email list growth: +15% MoM • Website conversion rate: ≥3.2% | - Launch teaser campaign across social media - Develop email nurture sequence - Optimize landing pages for conversions | $40,000 | Marketing Operations - Sarah Kim
Q2 - April to June | Establish primary digital marketing channels. | • Google Ads account active with 3 campaigns • Social media presence: 5K+ followers • Email list: +10,000 subscribers | - Set up Google Ads and Facebook Pixel - Create content calendar for monthly posts - Launch lead magnet offer | $25,000 | Digital Marketing Team - Tom Wilson
Q3: Full Launch & Performance Optimization
Q3 - July to September | Execute full-scale product launch and campaign rollout. | • 50,000 website visits/month • Conversion rate: ≥4.5% • CAC ≤ $25 | - Deploy paid advertising across channels - Host virtual launch event (1,000+ attendees) - Launch influencer collaboration program | $75,000 | Marketing Lead - Alex Turner
Q3 - July to September | Optimize marketing funnel based on performance data. | • 25% reduction in CAC • ROI ≥ 4:1 on paid campaigns • Increase in customer retention by 10% | - A/B test ad creatives and CTAs - Refine lead scoring model - Implement retargeting strategies | $30,000 | Data Analytics Team - Rachel Green
Q4: Scaling & Strategic Expansion
Q4 - October to December | Scale high-performing campaigns and enter new markets. | • 20% YoY growth in revenue • Expand presence in 2 new regions • Customer acquisition cost reduced by 30% | - Launch localized campaigns for international markets - Partner with regional distributors - Introduce referral program | $100,000 | Global Marketing Manager - James Reed
Q4 - October to December | Evaluate year-end performance and plan for next cycle. | • Complete annual marketing performance report • Benchmark KPIs against industry standards • Finalize Q1 2025 strategic roadmap | - Compile all campaign analytics - Host planning workshop with leadership team - Share results with stakeholders | $20,000 | Marketing Director - Lisa Brown
Total Annual Budget: |  |  |  | $315,000
Note: This template is designed for marketing planning within a business strategy framework. All figures and timelines are illustrative.