## Worksheet
Marketing Planning - Tracking View
Activity / Task | Owner | Start Date | Target End Date | Actual End Date | Status | Budget (USD) | Progress (%)
Market Research & Analysis | Marketing Team | 2024-01-05 | 2024-01-31 | - | In ProgressX | $12,500 | 65%
Competitor Benchmarking | Market Analysts | 2024-01-10 | 2024-01-31 | - | In ProgressX | $8,000 | 85%
Target Audience Segmentation | Marketing Strategist | 2024-01-15 | 2024-01-31 | - | In ProgressX | $6,000 | 75%
Marketing Campaign Development | Creative Team | 2024-02-01 | 2024-03-15 | - | In ProgressX | $25,000 | 40%
Content Creation & Production | Content Team | 2024-02-15 | 2024-03-31 | - | In ProgressX | $18,000 | 25%
Channel Strategy & Allocation | Media Planner | 2024-02-01 | 2024-03-15 | - | In ProgressX | $15,000 | 50%
Performance Metrics & KPIs Setup | Data Analyst | 2024-03-18 | 2024-03-31 | - | DelayedX | $5,000 | 15%