## Worksheet
Marketing Planning - Tracking View
Activity / Task | Owner | Start Date | End Date | Status | Budget (USD) | KPI Target | Action Items
Develop Campaign Strategy | Jane Smith | 2024-03-01 | 2024-03-15 | In Progress | $5,000 | Generate 1,500 leads | EditLog Update
Create Social Media Content Calendar | Mark Johnson | 2024-03-10 | 2024-04-15 | Pending | $3,500 | Post 8 times/week; 15% engagement increase | EditLog Update
Launch Paid Advertising Campaign | Lisa Chen | 2024-04-01 | 2024-05-31 | Pending | $25,000 | Reach 50,000 users; CPA under $1.50 | EditLog Update
Host Webinar: Product Launch Event | Robert Kim | 2024-05-10 | 2024-05-11 | Pending | $8,000 | Attendees: 300+; Conversion rate: 15% | EditLog Update
Finalize Post-Campaign Report | Sarah Davis | 2024-06-01 | 2024-06-15 | Pending | $1,500 | Document ROI, insights & recommendations | EditLog Update
Review and Approve All Deliverables | Michael Brown | 2024-05-31 | 2024-06-15 | Completed | $2,000 | All assets approved and archived | EditLog Update
Total Estimated Budget: |  |  |  |  | $45,000