## Worksheet
Task | Owner | Timeline & Status |  |  |  | Priority
|  | Start Date | Due Date | Status | Progress (%)
Market Research & Competitor Analysis | Jane Doe | 2024-01-05 | 2024-01-19 | In Progress | 65% | High
Create Brand Messaging & Positioning | John Smith | 2024-01-10 | 2024-01-26 | Pending | 0% | High
Develop Campaign Strategy (Digital & Print) | Sarah Johnson | 2024-01-15 | 2024-01-31 | Pending | 0% | High
Design Creative Assets (Banners, Posters) | Alex Brown | 2024-01-20 | 2024-02-10 | Pending | 0% | Medium
Finalize Media Buying Plan & Budget Allocation | Lisa White | 2024-01-25 | 2024-02-07 | Pending | 0% | High
Launch Campaign (Phase 1: Digital Channels) | Mark Lee | 2024-02-15 | 2024-03-01 | Pending | 0% | High
Track KPIs & Performance Metrics (Weekly) | Emily Carter | 2024-02-15 | Ongoing | Pending | 0% | High
Adjust Strategy Based on Real-Time Data | Jane Doe | 2024-03-05 | 2024-03-15 | Pending | 0% | High
Report Results & ROI Analysis (End of Campaign) | John Smith | 2024-03-16 | 2024-03-31 | Pending | 0% | High
Total Tasks: | [5 empty] | 10
Legend:
High– Critical tasks with immediate impact on campaign success
Medium– Important but less time-sensitive activities
Status:Pending, In Progress, Completed
Marketing Planning - Analysis View Chore Chart ¦ Generated on 2024-01-03