## Worksheet
Task | Responsible Team/Person | Deadline | Status | Notes / Comments
Develop marketing strategy for Q3 2024 | Marketing Director & Strategy Team | June 15, 2024 | Pending | Include digital and traditional channels.
Create social media content calendar | Social Media Manager | June 10, 2024 | In Progress | Include weekly posts for LinkedIn, Twitter, Instagram.
Design promotional banners and graphics | Graphic Design Team | June 20, 2024 | Pending | Ensure brand consistency.
Analyze competitor marketing campaigns | Market Research Analyst | June 5, 2024 | Completed | Data report submitted on June 6.
Launch email marketing campaign for new product | Email Marketing Specialist | July 1, 2024 | Pending | Segmented audience list required.
Set up and test Google Ads campaign | PPC Specialist | June 25, 2024 | Pending | Budget: $3,000.
Organize influencer partnership outreach | Influencer Relations Manager | July 10, 2024 | Pending | Target: 5 influencers in tech niche.
Host internal training session on new campaign tools | Training Coordinator | June 18, 2024 | Pending | All marketing staff required to attend.
Review and approve all campaign assets before launch | Marketing Director | July 3, 2024 | Pending | Final sign-off required.
Measure and report campaign KPIs post-launch | Data Analytics Team | August 1, 2024 | Pending | Track CTR, conversion rate, ROI.