## Worksheet
Task Name | Responsible Team | Start Date | End Date | Status | Priority | Budget (USD)
Market Research & Competitor Analysis | Marketing Research | 2024-03-01 | 2024-03-15 | In Progress | High | $8,500.00
Content Calendar Development | Content Team | 2024-03-16 | 2024-04-15 | Pending | High | $6,750.00
SEO Optimization Campaign Launch | SEO Specialists | 2024-03-18 | 2024-05-15 | Pending | Medium | $15,300.00
Design Social Media Visuals (Q2) | Graphic Design | 2024-03-15 | 2024-06-30 | Pending | Medium | $9,850.00
Email Marketing Campaign (Q2) | Email Marketing Team | 2024-04-10 | 2024-06-30 | Pending | High | $7,250.00
Trade Show Participation (April) | Events & PR Team | 2024-04-15 | 2024-04-18 | Pending | High | $35,500.00
Influencer Outreach Program (Q2) | Influencer Relations | 2024-04-15 | 2024-07-31 | Pending | Medium | $18,900.00
Performance Analytics & Reporting (Monthly) | Data Analytics Team | 2024-03-31 | Ongoing | Pending | High | $5,600.00 (Monthly)
Total Estimated Budget: | [5 empty] | $107,700.00