## Marketing Planning Chore Chart
Marketing Planning Chore Chart
Task ID | Task Description | Owner | Deadline | Status | Progress (%) | Budget (USD)
MKT-001 | Conduct Market Research & Competitor Analysis | Jane Smith | 2023-11-15 | Pending | 30% | $8,500
MKT-002 | Define Target Audience Personas | Mike Johnson | 2023-11-18 | Pending | 50% | $4,200
MKT-003 | Create Campaign Messaging Framework | Sarah Williams | 2023-11-22 | Pending | 75% | $6,800
MKT-004 | Design Social Media Content Calendar (Q1) | David Lee | 2023-11-25 | Pending | 40% | $5,000
MKT-005 | Develop Email Marketing Campaign Draft | Lisa Brown | 2023-11-30 | Pending | 25% | $7,000
MKT-006 | Finalize Budget Allocation & Approval | Robert Taylor | 2023-12-15 | Pending | 10% | $45,000
MKT-007 | Launch Pilot Campaign (Test Market) | Amy Garcia | 2023-12-20 | Pending | 0% | $18,500
MKT-008 | Review Performance Metrics & Optimize Strategy | Chris Moore | 2024-01-15 | Pending | 0% | $12,300
Total Estimated Budget:$107,300
Overall Progress:32% (Average of all tasks)