## Worksheet
Marketing Planning - Manager View
Task Name | Team Member | Due Date | Status | Priority | Budget Allocated ($) | Action Required(Manager Notes)
Content Calendar Development | Jane Doe | 2024-05-15 | In Progress | High | 1,200 | Review draft by 2024-05-13
Social Media Campaign Launch | John Smith | 2024-05-18 | Pending Approval | High | 3,500 | Approve creative assets by 2024-05-16
Email Marketing Sequence Design | Lisa Chen | 2024-05-17 | Not Started | Medium | 800 | Start on 2024-05-11
Event Sponsorship Outreach | Mike Brown | 2024-05-20 | In Progress | High | 5,000 | Contact 3 target sponsors by 2024-05-15
Market Research Analysis Report | Sarah Wilson | 2024-05-19 | Not Started | Medium | 1,800 | Begin data collection on 2024-05-13
SEO Optimization for Landing Pages | David Kim | 2024-05-16 | In Progress | Medium | 1,500 | Finalize keyword strategy by 2024-05-14
Analytics Dashboard Setup | Amy Patel | 2024-05-18 | Pending Review | High(Critical)
Total Budget Allocated: |  |  |  |  | $13,800