## Worksheet
Marketing Planning - Chore Chart
Multi-Page Template ¦ Q3 2024
Task/Activity | Owner | Due Date | Status | Priority
Create Q3 Marketing Strategy Document | Jane Doe - Marketing Manager | 2024-07-05 | In Progress | High
Design Social Media Campaign Graphics | Mike Chen - Graphic Designer | 2024-07-10 | To Do | High
Develop Email Marketing Series (3 emails) | Sarah Lee - Content Writer | 2024-07-12 | To Do | Medium
Analyze Competitor Campaigns (Q2) | David Kim - Marketing Analyst | 2024-07-08 | In Review | Medium
Update Brand Guidelines Document | Alice Thompson - Brand Manager | 2024-07-15 | To Do | Low
Schedule & Launch LinkedIn Campaign | James Wilson - Digital Marketing Specialist | 2024-07-18 | To Do | High
Conduct Target Audience Survey (Online) | Linda Brown - Market Researcher | 2024-07-14 | In Progress | Medium
Prepare Monthly Performance Report (Q3) | Raj Patel - Data Analyst | 2024-07-31 | To Do | Medium
Page 1 of 3 ¦ Marketing Planning Chore Chart ¦ Confidential
Marketing Planning - Chore Chart
Multi-Page Template ¦ Q3 2024 (Continued)
Task/Activity | Owner | Due Date | Status | Priority
Create YouTube Video Series (4 videos) | Chris Moore - Video Producer | 2024-07-25 | To Do | High
Optimize Landing Pages for Conversion | Tina Zhang - Web Developer | 2024-07-20 | In Progress | High
Coordinate Influencer Outreach Program | Nina Patel - PR Coordinator | 2024-07-30 | To Do | Medium
Plan & Book Trade Show Booth (Event: Sep 15) | Gregory Hall - Event Manager | 2024-08-01 | To Do | High
Generate Monthly ROI Report for Campaigns | Maria Gonzalez - Finance Analyst | 2024-08-05 | To Do | Medium
Review & Approve Final Campaign Materials (Pre-Launch) | Ben Carter - Creative Director | 2024-07-31 | To Do | High
Conduct Post-Campaign Review (Q2 Results) | Sophia Johnson - Marketing Strategist | 2024-07-16 | To Do | Medium
Update CRM with New Lead Data (Q3) | Daniel Lee - Sales Operations | 2024-07-30 | To Do | Low
Page 2 of 3 ¦ Marketing Planning Chore Chart ¦ Confidential
Marketing Planning - Chore Chart
Multi-Page Template ¦ Q3 2024 (Final)
Task/Activity | Owner | Due Date | Status | Priority
Set Up Google Analytics Goals & Events | Lisa Park - Web Analyst | 2024-08-05 | To Do | Medium
Create Customer Persona Refresh (Update & Validate) | Emma Wilson - UX Researcher | 2024-07-31 | To Do | Medium
Prepare Presentation for Leadership Review (Q3) | Claire Davis - Marketing Director | 2024-08-05 | To Do | High
Launch A/B Test for Email Subject Lines (3 variants) | Kevin Brown - Optimization Specialist | 2024-08-15 | To Do | Medium
Update Marketing Calendar with Q4 Planning (Draft) | Natalie Scott - Planning Coordinator | 2024-08-31 | To Do | Low
Secure Approval for Q4 Budget Proposal | Robert Evans - Finance Lead | 2024-08-30 | To Do | High
Conduct Team Feedback Session (Post-Q3) | Sarah Lee - HR Coordinator | 2024-09-05 | To Do | Low
Archive Q3 Campaigns & Documentation | James Wilson - Marketing Admin | 2024-09-10 | To Do | Low