## Worksheet
Marketing Planning Chore Chart - Office Use
Task | Owner | Deadline | Status | Progress (%) | Notes
Campaign Strategy Development | Marketing Team Lead | 2025-04-15 | In Progress | 65% | Finalizing target audience segments.
Social Media Calendar Creation | Social Media Manager | 2025-04-10 | Pending | 15% | Waiting on campaign assets.
Email Newsletter Design | Content Designer | 2025-04-12 | In Progress | 80% | Final review scheduled for tomorrow.
SEO Optimization Audit | Digital Marketing Analyst | 2025-04-18 | Pending | 5% | Waiting on access to analytics dashboard.
Event Planning: Trade Show Booth | Event Coordinator | 2025-04-20 | In Progress | 70% | Samples and promotional materials ordered.
Customer Feedback Survey Deployment | Market Research Specialist | 2025-04-14 | Pending | 10% | Draft finalizing.
Total Tasks: |  |  |  | 6
Overall Progress: |  |  |  | 54%