## Worksheet
Marketing Planning Chore Chart
Professional Template ¦ Purpose: Marketing Planning
Task / Activity | Owner | Due Date | Status | Priority
Define Marketing Goals for Q3 2024 | Jane Smith | 2024-06-15 | Complete | High
Conduct Competitive Analysis | Mark Johnson | 2024-06-20 | Pending | High
Create Customer Persona Profiles | Lisa Chen | 2024-06-18 | Pending | Medium
Develop Content Calendar (July) | Alex Rivera | 2024-06-25 | Pending | High
Launch Social Media Campaign (Phase 1) | Sarah Kim | 2024-07-05 | Pending | High
Analyze Campaign Performance (First Week) | David Lee | 2024-07-12 | Pending | Medium
Optimize Ad Spend Based on Data Insights | Maria Gonzalez | 2024-07-18 | Pending | High
Prepare Q3 Performance Report (Draft) | Jane Smith | 2024-07-25 | Pending | High
Plan Q4 Marketing Strategy Session | All Team Members | 2024-08-01 | Pending | Medium
Last Updated: June 5, 2024 ¦ Data Synced Automatically