## Worksheet
Task | Owner | Due Date | Status | Progress (%)
Market Research Phase
Competitor Analysis Report | Jane Smith | 2023-10-15 | Completed | 100%
Customer Survey Deployment | Mike Johnson | 2023-10-20 | Pending | 50%
Campaign Development
Content Calendar Creation | Sarah Lee | 2023-10-18 | Pending | 65%
Ad Creative Design (Social Media) | Daniel Brown | 2023-10-25 | Delayed | 30%
Launch Preparation
Email Marketing Sequence Setup | Lisa Chen | 2023-10-28 | Pending | 45%
Website Landing Page Optimization | Tom Wilson | 2023-11-01 | Pending | 75%
Report Version - Marketing Planning Chore Chart ¦ Generated on: