## Worksheet
Marketing Planning - Tracking View (Chore Chart)
Task Name | Owner | Due Date | Status | Progress (%) | Last Updated
Develop Content Calendar Q3 2024 | Jane Doe | 2024-07-15 | In Progress | 75% | 2024-06-18
Create Social Media Campaigns | Mike Smith | 2024-07-18 | Pending Review | 50% | 2024-06-16
Analyze Competitor Strategies | Sarah Johnson | 2024-07-10 | Completed | 100% | 2024-06-15
Design Email Newsletter Templates | Tony Lee | 2024-07-12 | In Progress | 60% | 2024-06-17
Launch Influencer Outreach Program | Lisa Wong | 2024-07-25 | Pending Start | 10% | 2024-06-14
Conduct Market Research Survey | Daniel Brown | 2024-07-31 | Pending Start | 5% | 2024-06-13
Prepare Launch Event Materials | Amy Garcia | 2024-08-05 | Pending Start | 0% | 2024-06-13
Note: This tracking view is designed for marketing planning chore management. Update statuses regularly for accurate progress tracking.