## Worksheet
Marketing Planning - Advanced Gantt Chart
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress (%)
MTK-001 | Market Research & Analysis | 2024-04-01 | 2024-04-15 | 15 | In Progress
MTK-002 | Target Audience Segmentation | 2024-04-16 | 2024-04-30 | 15 | Delayed
MTK-003 | Campaign Strategy Development | 2024-05-01 | 2024-05-15 | 15 | Not Started
MTK-004 | Creative Content Production | 2024-05-16 | 2024-06-15 | 31 | Blocked
MTK-005 | Multi-Channel Launch | 2024-06-16 | 2024-07-31 | 46 | Delayed
MTK-006 | Strategic Approval Sign-off | 2024-05-15 | Milestone
MTK-007 | Campaign Launch Day | 2024-06-16 | Milestone
MTK-008 | Performance Monitoring & Optimization | 2024-07-01 | 2024-12-31 | 184 | Not Started
MTK-009 | Final Campaign Report & Review | 2025-01-01 | 2025-01-31 | 31 | Pending