## Worksheet
Marketing Planning - Gantt Chart (Analysis View)
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress Timeline (Gantt)
MP-001 | Market Research & Analysis | 2024-03-01 | 2024-03-15 | 15 | Pending
MP-002 | Competitor Benchmarking | 2024-03-16 | 2024-03-31 | 16 | In Progress
MP-003 | Target Audience Segmentation | 2024-04-01 | 2024-04-15 | 15 | In Progress
MP-004 | Marketing Strategy Development | 2024-04-16 | 2024-05-15 | 30 | Pending
MP-005 | Content Creation & Design | 2024-05-16 | 2024-06-15 | 31 | Pending
MP-006 | Campaign Launch Preparation | 2024-06-16 | 2024-07-15 | 30 | Pending
MP-007 | Q3 Marketing Campaign Launch | 2024-07-16 | 2024-07-16 | 1 | Milestone
MP-008 | Performance Monitoring & Reporting | 2024-07-17 | 2024-11-30 | 137 | Pending
Total Duration: |  |  |  |  | 375 Days (from 2024-03-01 to 2024-11-30)