## Worksheet
Marketing Planning - Gantt Chart (Client View)
Task | Start Date | End Date | Status | Progress
Market Research & Analysis | 2024-01-15 | 2024-01-31 | In Progress
Competitor Benchmarking | 2024-01-18 | 2024-02-05 | In Progress
Target Audience Definition | 2024-01-30 | 2024-02-15 | Pending
Marketing Strategy Development | 2024-02-10 | 2024-03-15 | Pending
Content Creation (Phase 1) | 2024-03-01 | 2024-03-31 | Pending
Channel Planning (Social, Email, SEO) | 2024-03-15 | 2024-04-15 | Pending
Ad Campaign Launch (Test Phase) | 2024-04-15 | 2024-05-31 | Pending
Full Campaign Rollout | 2024-06-01 | 2024-08-31 | Pending
Q3 Marketing Review (Milestone) | 2024-09-15 | 2024-09-15 | Milestone Achieved
Performance Analytics & Reporting | 2024-10-01 | 2024-10-31 | Pending
Q4 Planning & Strategy Update | 2024-11-01 | 2024-12-31 | Pending
Total Timeline: | 2024-01-15 | 2024-12-31 | Marketing Plan Duration: 349 days
Note: This Gantt chart is a visual representation of the marketing planning timeline for Client View. Progress percentages are estimates and subject to change based on project updates.