## Worksheet
Marketing Planning Gantt Chart - Data Version
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | % Complete
T001 | Market Research & Analysis | 2024-04-01 | 2024-04-15 | 15 | In Progress | 75%
T002 | Define Target Audience | 2024-04-16 | 2024-04-30 | 15 | In Progress | 65%
T003 | Develop Marketing Strategy | 2024-05-01 | 2024-05-15 | 15 | Pending | 0%
T004 | Create Campaign Content (Copy & Creative) | 2024-05-16 | 2024-06-15 | 31 | Pending | 0%
T005 | Design Digital Assets (Social Media, Landing Pages) | 2024-06-16 | 2024-07-15 | 31 | Pending | 0%
M01 | Marketing Strategy Approval (Milestone) | 2024-05-15 | 2024-05-15 | 1 | Closed | 100%
T006 | Launch Campaign - Phase 1 (Digital Ads & Social Media) | 2024-07-16 | 2024-08-31 | 47 | Pending | 0%
T007 | Track Performance & Optimize Ads (Weekly) | 2024-08-15 | 2024-11-30 | 98 | Pending | 0%
M02 | Campaign Final Review & Reporting (Milestone) | 2024-11-30 | 2024-11-30 | 1 | Pending | 0%
T008 | Post-Campaign Analysis & Recommendations | 2024-12-01 | 2024-12-15 | 15 | Pending | 0%
T009 | Archive Campaign Files & Lessons Learned Documentation | 2024-12-16 | 2024-12-31 | 16 | Pending | 0%
Total Duration: |  |  |  | 328 days
Note: This Gantt Chart template is designed for marketing planning with a data-driven approach. All dates are in YYYY-MM-DD format. Status indicators and progress percentages can be updated as tasks progress.