## Worksheet
Marketing Planning - Detailed Gantt Chart
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Budget ($) | Timeline Progress (Gantt View)
MR-01 | Competitor Analysis | 2024-04-01 | 2024-04-15 | 15 | Completed | 8,500
TA-01 | Customer Persona Development | 2024-04-16 | 2024-05-15 | 30 | Completed | 6,800
SD-01 | Marketing Strategy Drafting | 2024-05-16 | 2024-06-15 | 30 | Completed | 9,750
CP-01 | Campaign Concept & Creative Development | 2024-06-16 | 2024-07-31 | 46 | Completed | 18,900
CP-02 | Content Creation (Video, Copy, Graphics) | 2024-07-01 | 2024-08-31 | 61 | Completed | 35,650
CP-03 | Channel Strategy & Allocation | 2024-08-15 | 2024-09-30 | 46 | Completed | 15,750
BG-01 | Budget Approval & Finalization | 2024-09-15 | 2024-10-31 | 46 | Completed | 7,850
EX-01 | Campaign Launch & Execution | 2024-10-01 | 2025-03-31 | 183 | Delayed (In Progress) | 98,500
MS-01 | Campaign Launch Day | 2024-10-05 | 2024-10-05 | 1 | Milestone Achieved | $- | ●
MR-02 | Performance Tracking & Weekly Reports | 2024-10-15 | 2025-03-31 | 179 | In Progress | $6,800 (est.)
OP-01 | Real-Time Campaign Optimization | 2024-11-05 | 2025-03-31 | 148 | In Progress | $7,950 (est.)
FE-01 | Post-Campaign Analysis & Reporting | 2025-04-01 | 2025-04-30 | 30 | Pending Start | $11,589 (est.)
Total Budget: | [5 empty] | $207,739
Note:This Gantt chart visualizes the detailed marketing planning timeline. Progress percentages are based on completed milestones.