## Worksheet
Marketing Planning - Extended Gantt Chart
Task | Start Date | End Date | Duration (Days) | Responsible Team | Status
Project Kickoff & Planning | 2024-01-05 | 2024-01-15 | 11 | Marketing Leadership | In Progress
Market Research & Analysis | 2024-01-16 | 2024-01-31 | 16 | Research Team | In Progress
Target Audience Segmentation | 2024-02-01 | 2024-02-15 | 15 | Data Analytics Team | In Progress
Brand Messaging Development | 2024-02-16 | 2024-03-15 | 30 | Creative & Copywriting Team | In Progress
Channel Strategy Planning (Digital, Print, TV) | 2024-03-16 | 2024-03-31 | 16 | Media Planning Team | In Progress
Budget Allocation & Approval | 2024-04-01 | 2024-04-15 | 15 | Finance & Leadership | In Progress
Content Creation (Videos, Banners, Blogs) | 2024-04-16 | 2024-05-31 | 46 | Creative Production Team | In Progress
Ad Campaign Launch (Phase 1) | 2024-06-01 | 2024-06-30 | 30 | Digital Marketing Team | In Progress
Performance Monitoring & Analytics Review | 2024-07-01 | 2024-07-31 | 31 | Data & Insights Team | In Progress
Ad Campaign Optimization (Phase 2) | 2024-08-01 | 2024-08-31 | 31 | Digital Marketing Team | In Progress
Final Reporting & ROI Analysis | 2024-09-01 | 2024-09-15 | 15 | Marketing Leadership & Finance | In Progress
Milestone: Campaign Completion & Handover | 2024-09-30 | 2024-09-30 | 1 | Marketing Leadership | Milestone Reached (Status)
75%
Note: This Gantt chart represents an extended marketing planning timeline. Dates are based on a projected Q1–Q3 2024 schedule. Progress percentages and statuses are illustrative and should be updated regularly.