## Worksheet
Task | Start Date | End Date | Responsible Team | Budget (USD) | Status | Progress (%)
Market Research & Analysis | 2024-01-05 | 2024-01-20 | Research & Insights | $15,000 | In Progress | 65%
Brand Positioning Strategy | 2024-01-18 | 2024-02-05 | Marketing Strategy | $18,500 | In Progress | 75%
Campaign Creative Development | 2024-02-01 | 2024-03-15 | Design & Content | $35,000 | Not Started | 15%
Digital Advertising Launch | 2024-03-10 | 2024-05-31 | Digital Marketing | $85,000 | Not Started | 5%
Social Media Campaigns (Q2) | 2024-04-01 | 2024-06-30 | Social Media Team | $45,000 | Not Started | 2%
Event Sponsorship & PR | 2024-05-15 | 2024-07-31 | PR & Events | $60,000 | Not Started | 1%
Milestone Review & Forecast Update | 2024-07-15 | 2024-07-31 | Marketing Leadership | $8,000 | Not Started | 0%
Total Budget: |  |  |  | $266,500