## Worksheet
Marketing Planning - Large Business Gantt Chart
Task Name | Start Date | End Date | Status | Progress (%)
Phase 1: Market Research & Analysis
Competitor Analysis | 2024-04-01 | 2024-04-15 | In Progress
Customer Segmentation Study | 2024-04-03 | 2024-04-18 | In Progress
Phase 2: Campaign Strategy & Planning
Campaign Goal Setting | 2024-04-16 | 2024-04-25 | Not Started
Phase 3: Content Development & Design
Creative Asset Production | 2024-04-18 | 2024-05-15 | In Progress
Phase 4: Launch Readiness & Testing
Channel Integration Testing | 2024-05-16 | 2024-05-31 | Not Started
Phase 5: Campaign Launch
Official Campaign Rollout | 2024-06-01 | 2024-06-30 | Not Started
Milestone: Launch Completion | 2024-06-30 | 2024-06-30 | Milestone Reached
Phase 6: Post-Launch Analysis & Optimization
Performance Reporting | 2024-07-01 | 2024-07-15 | Not Started
Marketing Planning Gantt Chart - Version 2.0 ¦ Updated on April 5, 2024