## Worksheet
Marketing Planning - Gantt Chart (Multi-Page)
Period: January 2024 - December 2024
Task / Activity | Month
| Jan | Feb | Mar | Apr | May | Jun 1-15[Phase A] | Jun 16-30[Phase B] | Jul | Aug | Sep | Oct | Nov | Dec 1-15[Phase C] | Dec 16-31[Phase D]
Q1 - Strategy & Planning
Market Research & Analysis | ✔
Competitor Benchmarking | ✔ |  | ✔
Target Audience Segmentation | ✔
Q2 - Campaign Development
Creative Asset Development |  |  | ✔ | ✔
Content Calendar Creation |  |  | ✔ | ✔
Channel Strategy Finalization |  |  |  | ✔ | ✔
Q3 - Campaign Launch & Execution
Phase A: Digital Ad Rollout |  |  |  |  | ✔ |  | ✔
Phase B: Influencer Partnerships |  |  |  | ✔ |  | ✔
Phase C: Email & Automation Setup |  |  |  | ✔ |  | ✔
Q4 - Optimization & Reporting
Performance Analytics Review | [5 empty] | ✔ |  | ✔
A/B Testing & Iteration |  |  |  |  | ✔ |  |  | ✔
Year-End Campaign Report & Forecasting |  |  |  |  | ✔ | [5 empty] | ✔
Document Version: 1.2 ¦ Prepared on: May 5, 2024 ¦ Marketing Department
Note: Each colored cell represents task progress. Light green indicates completed phases.
Marketing Planning - Gantt Chart (Page 2)
Resource Allocation & Dependencies Overview
Task | Team Responsible | Dependencies | Budget (USD) | Phase Indicator
Market Research & Analysis | Strategy Team | N/A | $5,000 | Q1 Phase 1
Competitor Benchmarking | Data Analytics Team | Market Research & Analysis Complete | $3,200 | Q1 Phase 2
Target Audience Segmentation | Customer Insights Group | Competitor Benchmarking Complete | $4,800 | Q1 Phase 3
Creative Asset Development | <Design & Video Team | Target Audience Segmentation Approved | $22,500 | Q2 Phase 1
Content Calendar Creation | Copywriting & Social Media Team | Creative Asset Development in Progress | $8,700 | Q2 Phase 2
Channel Strategy Finalization | Marketing Operations | Content Calendar Approved | $6,100 | Q2 Phase 3
Phase A: Digital Ad Rollout | Digital Marketing Team | Channel Strategy Finalized & Creative Assets Ready | $45,000 | Q3 Phase 1
Phase B: Influencer Partnerships | Influencer Relations Team | Phase A Launch Complete & Budget Allocated | $60,000 | Q3 Phase 2
Phase C: Email & Automation Setup | Email Marketing Team | Content Calendar Live & CRM Integration Complete | $18,300 | Q3 Phase 3
Performance Analytics Review | Data Science Team | All Campaigns Active for at least 2 Weeks | $12,000 | Q4 Phase 1
A/B Testing & Iteration | Marketing Ops & Data Team | Analytics Review Complete | $9,500 | Q4 Phase 2
Year-End Campaign Report & Forecasting | Strategy & Executive Team | A/B Testing Complete, Year-End Data Collected | $7,000 | Q4 Phase 3
Document Version: 1.2 ¦ Prepared on: May 5, 2024 ¦ Marketing Department - Page 2 of Multiple
Note: Dependencies are critical for timeline accuracy. Budgets are estimated.