## Worksheet
Marketing Planning Gantt Chart - One Page
Task | Start Date | End Date | Duration (Days) | Status
Project Initiation | 2024-04-01 | 2024-04-05 | 5
Market Research & Analysis | 2024-04-06 | 2024-04-15 | 10
Target Audience Definition | 2024-04-16 | 2024-04-18 | 3
Marketing Strategy Development | 2024-04-19 | 2024-04-30 | 12
Content Creation (Blog, Video, Social) | 2024-04-22 | 2024-05-10 | 19
Ad Campaign Design (Digital & Print) | 2024-05-01 | 2024-05-15 | 15
Media Planning & Booking | 2024-05-16 | 2024-05-31 | 16
Launch Event Planning & Logistics | 2024-06-01 | 2024-06-15 | 15
Milestone: Product Launch | 2024-06-16 | 2024-06-17 | 1
Post-Launch Performance Analysis | 2024-06-18 | 2024-07-31 | 44
Project Closure & Reporting | 2024-08-01 | 2024-08-05 | 5
Generated on April 5, 2024 ¦ Marketing Planning Gantt Chart - One Page Template