## Worksheet
Marketing Planning - Gantt Chart (Planning View)
Task | Start Date | End Date | Status | % Complete
Market Research & Analysis | 2024-01-05 | 2024-01-25 | In Progress | 75%
Define Target Audience | 2024-01-10 | 2024-01-15 | In Progress | 85%
Create Marketing Strategy | 2024-01-16 | 2024-01-30 | Pending | 5%
Develop Campaign Creative | 2024-01-31 | 2024-02-15 | Pending | 0%
Launch Digital Ads (Phase 1) | 2024-02-16 | 2024-03-15 | Pending | 0%
Campaign Launch Day | 2024-03-16 | 2024-03-16 | Milestone | 100%
Analyze Campaign Performance | 2024-03-17 | 2024-04-15 | Pending | 0%
Optimize & Scale Campaign | 2024-04-16 | 2024-05-31 | Pending | 0%
Gantt Chart View