## Worksheet
Marketing Planning Gantt Chart
Task ID | Task Description | Start Date | End Date | Duration (Days) | Status
T001 | Market Research & Analysis | 2024-04-01 | 2024-04-15 | 15 | In Progress
T002 | Target Audience Segmentation | 2024-04-16 | 2024-04-30 | 15 | In Progress
T003 | Develop Brand Messaging | 2024-05-01 | 2024-05-15 | 15 | Planned
T004 | Design Marketing Materials | 2024-05-16 | 2024-06-15 | 31 | Not Started
T005 | Launch Campaign (Phase 1) | 2024-06-16 | 2024-07-31 | 46 | Not Started
T006 | Monitor & Optimize Campaigns | 2024-08-01 | 2024-11-30 | 123 | Not Started
T007 | Final Performance Report | 2024-12-01 | 2024-12-31 | 31 | Not Started
This document is a printable version of the Marketing Planning Gantt Chart. Generated on: