## Worksheet
Marketing Planning - Professional Gantt Chart
Task ID | Task Name | Owner | Status | Start Date | End Date | Jan 2025 | Feb 2025 | Mar 2025 | Apr 2025 | May 2025 | Progress
1.1 | Market Research & Analysis | Jane Doe | In Progress | 01/05/2025 | 01/31/2025 | [5 empty] | 65%
1.2 | Competitor Benchmarking | John Smith | Pending | 02/01/2025 | 02/15/2025 | [5 empty] | 0%
2.1 | Campaign Strategy Development | Sarah Wilson | In Progress | 02/16/202503/10/2025 | [5 empty] | 78%
2.2 | Budget Allocation & Forecasting | Mike Brown | Pending | 03/11/202503/31/2025 | [6 empty] | 0%
3.1 | Campaign Launch | Team Lead | Milestone | 04/01/202504/01/2025 |  |  |  | ● Launch Day
4.1 | Digital Advertising Campaign | Lisa ChenIn Progress04/02/202505/31/2025 | [7 empty] | 47%
5.1 | Performance Reporting & Optimization | Daniel ReedPending06/01/202506/30/2025
Legend:
Task Header
Task Row
Milestone
Progress Bar